MyLivingCity  
Project Status Report #6

Sprint #3

|  |  |
| --- | --- |
| Period ending: | June 19 - June 27 |

|  |  |
| --- | --- |
| **Team Name** | **Number of Units completed** |
| Phuong (Jennifer) Tang-Tran | 16 |
| Joshua Sivertson | 19 |
| Changsin Park | 5 |
|  |  |

|  |  |
| --- | --- |
| **Client:** | Nic LeBlanc |

**At the end of this week:**

|  |  |
| --- | --- |
| Number of units remaining in backlog | 192 |
| Number of units in progress | 15 |
| Number of units in review | 0 |
| Number of units completed this week | 30 |
| Number of new units identified (additional scope) | 3 |

**Describe any tasks that could not be completed and how these is being addressed:**

|  |  |
| --- | --- |
| **Task** | **How is this being addressed?** |
| Setting up notification | Researching more about notifications from React libraries |
|  |  |

**Descripted any tasks that could not be completed and the impact:**

|  |  |
| --- | --- |
| **Task** | **Impact** |
| Setting up notification | low |
|  |  |

**Provide a schedule of this week's meetings and a summary.  Include agenda, minutes.**

Sunday – Retrospective Meeting to improve team’s productivity (1 hour)

Monday – Stand up meeting (30 mins)

Thursday – Check in meeting with Ben (10 mins)

Thursday – Check in meeting with Katie (5 mins)

Friday – Sponsor Meeting with Nic (1 hour)

**At the end of each sprint (even numbered weeks), include everything above and the following:**

1. Project end date as estimated at the end of last sprint (based on burn-up chart)

End of Sprint 6

1. Project end date as estimated at the end of this sprint (based on burn-up chart)

Halfway of Sprint 6

1. Estimated unit completion target for this sprint

40 units

1. Achieved unit completion target for this sprint.

47 units

1. Provide context for any loss or gain in productivity

Changed the way we looked at tasks and split then up into their roles for example (Front-End and Back-end) this significantly improved our productivity.

1. Estimated unit completion target for next sprint.  If different, please explain justification.

40

1. Attach a list of tasks addressed in the current sprint and their current state, assigned resource and estimate.

A screenshot of a cell phone

Description automatically generated

1. Attach a picture of your completed burn up chart.

A picture containing text, map, white, table

Description automatically generated